## Document History Log
| HHSC UNIFORM MANAGED CARE MANUAL |  | CHAPTER
5.26.1
| STAR Kids Contract Requirements Matrix for Medicaid Services Section 7 Transitional Phase Requirements |  | EFFECTIVE DATE
2020-02-14
Version 2.0.1
DOCUMENT HISTORY LOG
STATUS1 | DOCUMENT REVISION2 | EFFECTIVE DATE | DESCRIPTION3
Baseline | 2 | 2019-11-25 | Initial version Uniform Managed Care Manual Chapter 5.26.1 "STAR Kids Contract Requirements Matrix for Medicaid Services Section 7 Transitional Phase Requirements." Chapter 5.26.1 applies to the contract issued as a result of HHSC RFP number 529-13-0071.
Revision | 2.0.1 | 2020-02-14 | Accessibility approved version posted.
1 Status should be represented as “Baseline” for initial issuances, “Revision” for changes to the Baseline version, and “Cancellation” for withdrawn versions.
2 Revisions should be numbered according to the version of the issuance and sequential numbering of the revision—e.g., “1.2” refers to the first version of the document and the second revision.
3 Brief description of the changes to the document made in the revision.

## SK Req. Matrix_Sec 7
STAR Kids Contract Requirements Matrix for Medicaid Services Section 7 Transitional Phase Requirements
Contract Reference | Section Title | Requirement # | Performance Standard/Requirement | Frequency
TRANSITIONAL PHASE REQUIREMENTS
TRANSITION PHASE SCOPE
7.2 | Transition Phase Scope | TP-1 | The MCO must meet the Readiness Review requirements established by HHSC no later than 90 days prior to the Operational Start Date. | Ongoing
TRANSITIONAL PHASE SCHEDULE AND TASKS
7.3 | Transition Phase and Schedule and Tasks | TP-2 | The MCO must complete the Transition Phase no later than the Operational Start Date. | Ongoing
7.3 | Transition Phase and Schedule & Tasks | TP-3 | The MCO must clearly specify and request information needed from HHSC, other HHSC contractors, and Providers in a manner that does not delay the schedule or work to be performed. | Ongoing
CONTRACT START-UP & PLANNING
7.3.1 | Contract Start-Up & Planning | TP-4 | The MCO must develop a written work plan, referred to as the Transition/Implementation Plan. | Ongoing
7.3.1 | Contract Start-Up & Planning | TP-5 | The MCO must update the Transition/Implementation Plan provided with its proposal to HHSC no later than 30 days after the contract's effective date. | Ongoing
7.3.1 | Contract Start-Up & Planning | TP-6 | The MCO must provide monthly implementation progress reports through the sixth month of MCO program operations. | Ongoing
7.3.1 | Contract Start-Up & Planning | TP-7 | The MCO must include a detailed description of the process it will use to ensure continued authorization of Community-based Services at the time of implementation within the Transition/Implementation Plan. | Ongoing
7.3.1 | Contract Start-Up & Planning | TP-8 | The MCO's Transition/Implementation Plan must identify a designated MCO staff member responsible for the facilitation and oversight of this process. | Ongoing
ADMINISTRATION/KEY MCO PERSONNEL
7.3.2 | Administration/Key MCO Personnel | TP-9 | The MCO must designate and identify Key MCO Personnel that meet requirements in Attachment A, "STAR Kids Contract Terms" no later than the effective date of the contract. | Ongoing
7.3.2 | Administration/Key MCO Personnel | TP-10 | The MCO must supply HHSC with resumes of each Key MCO Personnel as well as organizational information that has changed relative to the MCO's Proposal. | Ongoing
7.3.2 | Administration/Key MCO Personnel | TP-11 | The MCO must provide information on the anticipated maximum caseload per Service Coordinator (i.e. # of member per Service Coordinator). | Ongoing
7.3.2 | Administration/Key MCO Personnel | TP-12 | The MCO must provide organizational charts for all material subcontractors. | Ongoing
MATERIAL SUBCONTRACTORS
7.3.2.1 | Material Subcontractors | TP-13 | The MCO must conduct, at a minimum, one annual site visit to each Materials Subcontractor per Contract Year. | Ongoing
7.3.2.1 | Material Subcontractors | TP-14 | The MCO must use a standard site visit tool. | Ongoing
7.3.2.1 | Material Subcontractors | TP-15 | The MCO must review policies, procedures, and applicable files and interview Material Subcontractor staff during each site visit. | Ongoing
7.3.2.1 | Material Subcontractors | TP-16 | The MCO must maintain a monitoring plan for each Material Subcontractor to include at a minimum: 1. the requirements for performance of all delegated functions with which the entity must comply; 2. the MCO’s responsibilities for the financial oversight of a Material Subcontractor who has an at-risk contract with the MCO for the provision of covered services; 3. required and periodic reporting and interfaces with Material Subcontractors required to perform an administrative function on behalf of the MCO; 4. a review of the entity’s solvency status, financial operation, and amounts paid for Covered Services (if applicable); and 5. a review of the entity’s contract compliance, logged complaints, and functional performance measurements. | Ongoing
7.3.2.1 | Material Subcontractors | TP-17 | The MCO must maintain quarterly and annual documentation as to the compliance of the Material Subcontractor with all requirements defined in the monitoring plan. | Ongoing
7.3.2.1 | Material Subcontractors | TP-18 | The MCO must require periodic reporting from each Material Subcontractor. | Ongoing
7.3.2.1 | Material Subcontractors | TP-19 | The MCO will monitor each reporting entity to ensure accurate and timely deliverables. | Ongoing
7.3.2.1 | Material Subcontractors | TP-20 | The MCO will meet with each Material Subcontractor on a regular basis to discuss any issues that may exist and include key personnel and designated staff by functional area and their Material Subcontractor counterparts. | Ongoing
7.3.2.1 | Material Subcontractors | TP-21 | The MCO must allow HHSC to attend meetings between the MCO and its Material Subcontractors and to receive the minutes from these meetings. | Ongoing
ORGANIZATIONAL AND FINANCIAL READINESS REVIEW
7.3.3. | Organizational and Financial Readiness Review | TP-22 | The MCO must update the organizational and financial information submitted in its proposal for any awarded Contract. | Ongoing
SYSTEM TESTING AND TRANSFER OF DATA
7.3.4 | System Testing and Transfer of Data | TP-23 | The MCO must have hardware, software, network and communications systems with the capability and capacity to handle and operate all MIS systems and subsystems identified in Section 8.1.20. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-24 | The MCO must accept into its system any and all necessary data files and information available from HHSC or its contractors. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-25 | The MCO will install and test all hardware, software, and telecommunications required to support the Contract. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-26 | The MCO will define and test modifications to the MCO’s system(s) required to support the business functions of the Contract. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-27 | The MCO will produce data extracts and receive all electronic data transfers and transmissions. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-28 | The MCO must develop resolution procedures to address problems identified or deficiencies in any data transmissions if any errors or deficiencies are evident. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-29 | The MCO will provide HHSC, or a designated vendor, with test data files for systems and interface testing for all external interfaces. | Ongoing
7.3.4 | System Testing and Transfer of Data | TP-30 | The MCO will demonstrate its system capabilities and adherence to Contract specifications during readiness review. | Ongoing
SYSTEM READINESS REVIEW
7.3.5 | System Readiness Review | TP-31 | The MCO must assure that systems services are not disrupted or interrupted during the Operations Phase of the Contract. | Ongoing
7.3.5 | System Readiness Review | TP-32 | The MCO must coordinate with HHSC and other contractors to ensure business and systems continuity for the processing of all health care claims and data as required under the Contract. | Ongoing
7.3.5 | System Readiness Review | TP-33 | The MCO must submit descriptions of interface and data and process flow for each key business processes described in Section 8.1.20.3 “System-wide Functions” to HHSC. | Ongoing
7.3.5 | System Readiness Review | TP-34 | The MCO must clearly define and document the policies and procedures that will be followed to support day-to-day systems activities. | Ongoing
7.3.5 | System Readiness Review | TP-35 | The MCO must develop, and submit for State review and approval, the following information no later than 120 Days prior to the Operational Start Date: 1. Disaster Recovery Plan; 2. Business Continuity Plan; 3. Security Plan; 4. Joint Interface Plan; 5. Risk Management Plan; and 6. Systems Quality Assurance Plan. ** Business Continuity Plan & Disaster Recovery Plan may be combined. | Ongoing
DEMONSTRATION AND ASSESSMENT OF SYSTEM READINESS
7.3.6 | Demonstration and Assessment of System Readiness | TP-36 | The MCO must provide documentation on systems and facility security and provide evidence or demonstrate that it is compliant with HIPAA and the HITECH Act. | Ongoing
7.3.6 | Demonstration and Assessment of System Readiness | TP-37 | The MCO must provide HHSC with a summary of all recent external audit reports, including findings and corrective actions, relating to the MCO’s proposed systems, including any SSAE16 audits that have been conducted in the past three years. | Ongoing
7.3.6 | Demonstration and Assessment of System Readiness | TP-38 | The MCO must promptly make additional information on the detail of these system audits available to HHSC upon request. | Ongoing
7.3.6 | Demonstration and Assessment of System Readiness | TP-39 | The MCO must be prepared to assure and demonstrate system readiness. | Ongoing
7.3.6 | Demonstration and Assessment of System Readiness | TP-40 | The MCO must execute system readiness test cycles to include all external data interfaces, including those with the MCO’s Pharmacy Benefits Manager (PBM) and other Material Subcontractors. | Ongoing
7.3.6 | Demonstration and Assessment of System Readiness | TP-41 | The MCO must provide a Corrective Action Plan in response to any Readiness Review deficiency no later than 10 Days after notification of any deficiency by HHSC. | Ongoing
OPERATIONS READINESS
7.3.7 | Operations Readiness | TP-42 | The MCO must clearly define and document the policies and procedures that will be followed to support day-to-day business activities related to the provision of STAR Kids Services, including coordination with contractors. | Ongoing
7.3.7 | Operations Readiness | TP-43 | The MCO will be responsible for developing and documenting its approach to quality assurance. | Ongoing
7.3.7 | Operations Readiness | TP-44 | MCO is responsible for all reasonable travel costs incurred by HHSC or its authorized agent for onsite Readiness Reviews. | Ongoing
7.3.7 | Operations Readiness | TP-45 | The MCO must develop new, or revise existing, operations procedures and associated documentation to support the MCO’s proposed approach to conducting operations activities in compliance with the contracted Scope of Work. | Ongoing
7.3.7 | Operations Readiness | TP-46 | The MCO must submit a list of all contracted and credentialed Providers to HHSC, in an HHSC-approved format, including a description of additional contracting and credentialing activities scheduled to be completed before the Operational Start Date. The list must include a specific section on home health providers. The section must also include estimates of STAR Kids Members who may require Private Duty Nursing and attendant services and evidence of provider adequacy to serve the eligible population. | Ongoing
7.3.7 | Operations Readiness | TP-47 | The MCO must prepare and implement a Member Services staff training curriculum and a Provider training curriculum, and provide documentation demonstrating compliance with training requirements (e.g., enrollment or attendance rosters dated and signed by each attendee or other written evidence of training.) All provider training and education materials and associated presentations specific to Medicaid benefits, services and programs must be submitted to HHSC for approval prior to use. | Ongoing
7.3.7 | Operations Readiness | TP-48 | The MCO must prepare a Coordination Plan documenting how the MCO will coordinate its business activities with those activities performed by the Department of Aging and Disability Services (DADS), HHSC contractors, the MCO’s PBM, and other Material Subcontractors, if any. The Coordination Plan will include identification of coordinated activities and protocols for the Transition Phase. | Ongoing
7.3.7 | Operations Readiness | TP-49 | The MCO must develop and submit the draft Member Handbook, draft Provider Manual, draft Provider Directory, and draft Member Identification Card to HHSC for review and approval. The materials must at a minimum meet the requirements specified in Section 8.1.5.1 and include the Critical Elements as defined in the Uniform Managed Care Manual (UMCM) Chapters 3.13, 3.14, 3.15, and 3.16. | Ongoing
7.3.7 | Operations Readiness | TP-50 | The MCO must develop and submit all other Provider Materials relating to Medicaid to HHSC prior to use or mailing. If HHSC has not responded to MCO’s request for review within 15 Business Days, the MCO may use the submitted materials. HHSC reserves the right to require discontinuation or correction of any Provider Materials that are not in compliance with state and federal laws or the Contract’s requirements. | Ongoing
7.3.7 | Operations Readiness | TP-51 | The MCO must develop and submit the MCO’s proposed Member complaint and appeals processes to HHSC. | Ongoing
7.3.7 | Operations Readiness | TP-52 | The MCO must provide sufficient copies of the final Provider Directory to the HHSC Administrative Services Contractor in sufficient time to meet the enrollment schedule. | Ongoing
7.3.7 | Operations Readiness | TP-53 | The MCO must demonstrate toll-free telephone systems and reporting capabilities for the Nurse Hotline, Member hotline, the Behavioral Health hotline, and the Provider hotline. | Ongoing
7.3.7 | Operations Readiness | TP-54 | The MCO must submit a Service Coordination plan that addresses requirements provided in Section 8.1.38.6. | Ongoing
7.3.7 | Operations Readiness | TP-55 | The MCO must submit a written Fraud, Waste, and Abuse Compliance Plan to HHSC for approval no later than 30 Days after the Contract Effective Date. See Section 8.1.21, Fraud, Waste, and Abuse, for the requirements of the plan, including new requirements for special investigation units. | Ongoing
7.3.7 | Operations Readiness | TP-56 | The MCO must submit a written plan to HHSC for providing pharmacy services, including proposed policies and procedures for: a. routinely updating formulary data following receipt of HHSC’s daily files (within two Business Days and off-cycle upon HHSC’s request); b. prior authorization of drugs, including how HHSC’s preferred drug lists (PDLs) will be incorporated into prior authorization systems and processes. The MCO must adopt HHSC’s prior authorization processes, criteria, and edits unless HHSC grants a written exception, and HHSC’s approval is required for all Clinical Edit policies; c. implementing drug utilization review; d. monitoring the use of psychotropic medications; e. overriding standard drug utilization review criteria and clinical edits when Medically Necessary based on the individual Member’s circumstances (e.g., overriding quantity limitations, drug-drug interactions, refill too soon); f. call center operations, including how the MCO will ensure that staff for all appropriate hotlines are trained to respond to prior authorization inquiries and other inquiries regarding pharmacy services; and g. monitoring the PBM Subcontractor. | Ongoing
7.3.7 | Operations Readiness | TP-57 | The MCO must include a written attestation by the PBM Subcontractor in the plan stating, in the three years preceding the Contract’s Effective Date, the PBM Subcontractor has not been: (1) convicted of an offense involving a material misrepresentation or any act of fraud or of another violation of state or federal criminal law; (2) adjudicated to have committed a breach of contract; or (3) assessed a penalty or fine of $500,000 or more in a state or federal administrative proceeding. | Ongoing
7.3.7 | Operations Readiness | TP-58 | The MCO must promptly alert HHSC of deficiencies, and must correct a deficiency or provide a Corrective Action Plan or Risk Mitigation Plan no later than ten Days after HHSC’s notification of deficiencies. | Ongoing
VALUE-ADDED SERVICES
7.3.7.1 | Value-Added Services | TP-59 | The MCO must use HHSC’s template for submitting proposed Value-added Services which is included in UMCM Chapter 4.16 “Value-added Services, Flexible Benefits, and Rewards and Incentives Template and Instructions.” | Ongoing
ASSURANCE OF SYSTEM AND OPERATIONAL READINESS
7.3.8 | Assurance of System and Operational Readiness | TP-60 | The MCO must assure HHSC that all processes, MIS systems, and staffed functions are ready and able to successfully assume responsibilities for operations prior to the Operational Start Date. | Ongoing
7.3.8 | Assurance of System and Operational Readiness | TP-61 | The MCO must assure that Key MCO Personnel, Member Services staff, Provider Services staff, and MIS staff are hired and trained, MIS systems and interfaces are in place and functioning properly, communications procedures are in place, Provider Manuals have been distributed, and that Provider training sessions have occurred according to the schedule approved by HHSC. | Ongoing
TDI AND CENTERS FOR MEDICARE AND MEDICAID SERVICES LICENSURE, CERTIFICATION, OR APPROVAL
7.3.9 | TDI and Centers for Medicare and Medicaid Services Licensure, Certification, or Approval | TP-62 | The MCO must receive TDI licensure, certification, or approval (as applicable) for all zip codes in the awarded Service Areas no later than 60 Days after the Contract’s Effective Date. | Ongoing
POST-TRANSITION
7.3.10 | Post-Transition | TP-63 | The MCO will work with HHSC, Providers, and Members to promptly identify and resolve problems identified after the Operational Start Date and to communicate to HHSC, Providers, and Members, as applicable. | Ongoing
7.3.10 | Post-Transition | TP-64 | The MCO must meet with HHSC staff and discuss post-Transition Phase issues and problems | Ongoing
7.3.10 | Post-Transition | TP-65 | The MCO must work proactively and collaboratively to resolve issues or problems identified by the Provider community, Members, Members’ families, and other stakeholders. | Ongoing
7.3.10 | Post-Transition | TP-66 | The MCO must work proactively and collaboratively to resolve issues or problems identified by the Provider community, Members, Members’ families, and other stakeholders. | Ongoing
7.3.10 | Post-Transition | TP-67 | The MCO must document the problems and their causes encountered during start-up and implementation in writing, and provide information regarding steps to correct the problem, including resources that will be used, the timeline for correcting the problem, the steps that the MCO will take to prevent the issue or problem from recurring, and document when the problem is resolved. | Ongoing
7.3.10 | Post-Transition | TP-68 | The MCO will report this information to HHSC every 14 Days, or as often as determined necessary by HHSC, during the first six months of operations, at which time HHSC will reassess the required frequency of providing this report. | Ongoing

## Template Definitions
Contract Reference: | Reference in the Star Health RFP where the performance requirement is located.
Section Title: | Name of the area in which the requirement is under within the RFP reference.
Requirement #: | Number of the requirement standard within the RFP. If no number is present, the standard # will be listed as N/A and the page number (if available) of where the standard is documented within the contract is listed under the Section Title column.
Performance Standard/Requirement: | Description of the requirement in the RFP, Change Order Request, or Amendment.
Frequency: | How often the standard will be evaluated/monitored. The priority determines the frequency of the monitoring.